# THAILAND DATA CENTER PERMITTING GUIDE - NAVIGATION & INDEX

**Complete Permit Documentation Package for Hyperscale Data Center Development**

---

# DOCUMENT OVERVIEW

This package contains comprehensive guidance on all permits and approvals required for data center development in Thailand. Documents are organized by complexity and implementation detail level.

## Documents in This Package

---

# WHERE TO START

## If you have 15 minutes: Quick Overview

1. Read this document (Navigation Guide)

2. Review "Typical Project Timeline" section below

3. Check "Critical Permits by Project Phase" section

**Outcome:** Understanding of which permits are needed and general sequence

## If you have 1 hour: Permit Screening

1. Read MASTER Guide: Section 1 (BOI Overview)

2. Read MASTER Guide: Section 2 (FBL Overview)

3. Read MASTER Guide: Section 8 (EIA Overview)

4. Review MASTER Guide: Section 11 (Timeline) and Section 12 (Costs)

**Outcome:** Understanding of scope, timeline, and cost requirements

## If you are ready to implement: Deep Dive

1. Start with MASTER Guide - read in full

2. For each permit, reference the detailed guide:

- BOI: Review MASTER Part 1 + Detailed BOI section (in Master)

- FBL: Review `PERMIT_02_FOREIGN_BUSINESS_LICENSE_DETAILED.md`

- EIA: Review `PERMIT_03_ENVIRONMENTAL_IMPACT_ASSESSMENT_DETAILED.md`

3. Create implementation project plan based on Section 11 (Timeline)

4. Assign responsibilities and deadlines

**Outcome:** Ready to begin permit applications with detailed guidance for each step

---

# CRITICAL PERMITS BY PROJECT PHASE

## PHASE 1: PRE-INVESTMENT PLANNING (Months 0-2)

**Primary Permits to Initiate:**

1. **BOI Promotion Certificate** (Master: Part 1)

- Status: Critical path item

- Timeline: 16 weeks from application

- Start: Immediately

- Action: Begin preparing documents now

2. **EIA Screening** (Master: Part 8 + Detailed Guide: Permit 03)

- Status: Critical path item

- Timeline: 6-8 months from screening approval

- Start: Month 1-2 (early site assessment)

- Action: Assess site sensitivity, determine if full EIA required

3. **Company Registration & Tax ID** (Master: Part 2)

- Status: Prerequisite for all other permits

- Timeline: 1-2 weeks

- Start: Week 1

- Action: Incorporate Thai company, get tax ID

4. **Site/Land Preparation** (Master: Part 3)

- Status: Prerequisite for construction permits

- Timeline: 1-7 months (depends on ownership/lease status)

- Start: Month 1 (parallel with BOI application)

- Action: Acquire land/lease, obtain title documents

**Key Decisions to Make in Phase 1:**

Foreign ownership structure (determines FBL requirement)

Data center category (8.2.1.1 vs. 8.2.1.2)

Preferred location (determines environmental requirements)

Capacity and technology specifications

---

## PHASE 2: PRE-CONSTRUCTION (Months 3-8)

**Primary Permits to Complete:**

1. **BOI Promotion Certificate** (Continued from Phase 1)

- Status: Should be approved by Month 4-8

- Action: Finalize application, respond to information requests

2. **Environmental Impact Assessment** (Continued from Phase 1)

- Status: Should be approved by Month 6-8 (if full EIA required)

- Action: Finalize EIA study, support public consultation

3. **Foreign Business License** (Master: Part 2 + Detailed Guide: Permit 02)

- Status: Can start after BOI approval

- Timeline: 8-12 weeks from initiation

- Start: Month 4-5 (after BOI approval)

- Action: Prepare FBL application with BOI proof

4. **Building Permit & Zoning** (Master: Part 3)

- Status: Can start after EIA approval

- Timeline: 6-10 weeks

- Start: Month 6-7 (after EIA approval)

- Action: Finalize architectural designs, submit building permit

---

## PHASE 3: CONSTRUCTION (Months 9-24)

**Primary Permits to Obtain:**

1. **Construction License** (Master: Part 3)

- Status: Prerequisite to construction start

- Timeline: 1-2 weeks (after contractor selection)

- Start: Month 8-9 (before construction)

- Action: Hire contractor, obtain construction license

2. **Electrical Design Approval** (Master: Part 4)

- Status: Before electrical installation

- Timeline: 4-8 weeks

- Start: Month 8-9

- Action: Submit electrical designs to authorities

3. **Power Utility Connection** (Master: Part 4)

- Status: Arrange during construction, activate before operations

- Timeline: 8-16 weeks (can be concurrent with construction)

- Start: Month 6-7

- Action: Submit connection request, arrange infrastructure upgrades

4. **Water Connection & Wastewater Permits** (Master: Part 5)

- Status: Arrange during construction, activate before operations

- Timeline: 6-10 weeks

- Start: Month 7-8

- Action: Request water connection, obtain wastewater permit

5. **Generator License** (Master: Part 4)

- Status: Before generator installation

- Timeline: 4-8 weeks

- Start: Month 9-10

- Action: Submit generator specifications for licensing

6. **Work Permits for Foreign Staff** (Master: Part 7)

- Status: Before foreign employees arrive

- Timeline: 1-2 weeks per employee

- Start: Month 8 (before staff relocation)

- Action: Initiate work permit applications for key personnel

---

## PHASE 4: PRE-OPERATIONS (Months 24-30)

**Primary Permits/Certifications to Complete:**

1. **Final Fire Safety Certification** (Master: Part 3)

- Status: Before occupancy

- Timeline: 1-2 weeks (final inspection)

- Start: Month 28-29

- Action: Request final fire safety inspection

2. **Electrical Final Certification** (Master: Part 4)

- Status: Before operations

- Timeline: 1-2 weeks (final inspection)

- Start: Month 28-29

- Action: Request final electrical inspection

3. **Occupancy Permit** (Master: Part 3)

- Status: Before commencing operations

- Timeline: 1-2 weeks

- Start: Month 29

- Action: Apply for occupancy permit from local authority

4. **Utility Activation** (Master: Part 4-5)

- Status: Before operations

- Timeline: Varies (depends on infrastructure readiness)

- Start: Month 28-29

- Action: Activate electricity, water, telecom services

---

## PHASE 5: ONGOING OPERATIONS (Month 30+)

**Continuous Compliance & Reporting:**

1. **BOI Annual Reporting** (Master: Part 1, Section 1.16)

- Frequency: Annually

- Requirement: Compliance reporting to BOI

- Documents: Financial statements, investment progress, environmental status

2. **Environmental Monitoring & Reporting** (Master: Part 5, Section 5.5)

- Frequency: Monthly (Year 1), Quarterly (Years 2-5), Annual (Year 6+)

- Requirement: Monitoring reports to pollution control agencies

- Documents: Water/air quality test results, emissions reports

3. **Work Permit Renewals** (Master: Part 7)

- Frequency: Annually per employee

- Requirement: Renewal applications for foreign staff

- Documents: Updated employment contracts, salary documentation

4. **Facility Certifications** (Master: Part 3)

- Frequency: Annually

- Requirement: Fire safety, electrical safety certifications

- Documents: Inspection reports, maintenance records

5. **Tax Compliance** (Master: Part 12)

- Frequency: Annually

- Requirement: Tax returns, BOI-related tax declarations

- Documents: Audited financial statements, tax returns

---

# PERMIT DEPENDENCY MAP

```

MONTH 0-2: FOUNDATION

├─ Company Registration (1-2 weeks)

├─ Tax ID Registration (immediately)

├─ Site Assessment & Acquisition (1-7 months)

├─ BOI Preliminary Consultation ✓

└─ EIA Screening Assessment ✓

MONTH 2-8: PRE-CONSTRUCTION

├─ BOI Application & Approval (4-8 months from filing) ✓

├─ EIA Study & Approval (6-8 months from TOR)

│  └─ Prerequisite: EIA Screening Certificate

├─ FBL Application & Approval (8-12 weeks from filing)

│  └─ Prerequisite: BOI Approval Certificate

├─ Building Permit Application (6-10 weeks from submission)

│  └─ Prerequisite: EIA Approval Certificate

└─ Land Title/Lease Finalization

MONTH 8-14: PRE-CONSTRUCTION CONTINUATION

├─ Construction License (1-2 weeks from contractor selection)

├─ Electrical Design Approval (4-8 weeks)

├─ Power Utility Connection (8-16 weeks)

├─ Water Connection & Permits (6-10 weeks)

├─ Generator License (4-8 weeks)

├─ Telecom/Network Permits (if applicable)

└─ Work Permits for Foreign Staff (1-2 weeks per employee)

MONTH 14-28: CONSTRUCTION

├─ Construction Supervision & Compliance

├─ Environmental Monitoring (monthly during construction)

├─ Utility Infrastructure Installation

├─ Safety & Fire System Installation

└─ Systems Integration & Testing

MONTH 28-30: PRE-OPERATIONS

├─ Final Fire Safety Inspection & Certification

├─ Final Electrical Inspection & Certification

├─ Final Environmental Clearance

├─ Occupancy Permit

├─ Utility Activation

└─ Staff Training & Readiness

MONTH 30+: OPERATIONS & COMPLIANCE

├─ Annual BOI Reporting

├─ Environmental Monitoring & Reporting

├─ Work Permit Renewals

├─ Annual Facility Certifications

└─ Tax Compliance & Reporting

```

---

# CRITICAL PATH ANALYSIS

**Longest Duration Items (Determine Overall Project Timeline):**

1. **EIA Approval** (6-8 months)

- Cannot start: Building Permit

- Cannot start: Construction

- Mitigation: Start EIA screening immediately (Month 1)

2. **BOI Approval** (4-8 months)

- Cannot start: FBL Application, Utility Connections

- Mitigation: Start BOI preparation immediately (Month 1)

3. **Construction** (12-18 months)

- Dependent on: Building Permit, Construction License

- Mitigation: Finalize designs early, secure contractor early

4. **Building Permit** (6-10 weeks)

- Dependent on: EIA Approval

- Mitigation: Prepare designs in parallel with EIA

**Critical Path = EIA → Building Permit → Construction**

**Parallel Fast Track = BOI + FBL Processing during EIA**

**Typical Total Project Duration:** 24-32 months from first step to operations

---

# KEY CONTACTS QUICK REFERENCE

## Government Agencies

---

# DOCUMENT-BY-DOCUMENT READING GUIDE

## For BOI Application Process

**Read in This Order:**

1. MASTER Guide, Part 1: BOI Overview (15 min)

2. MASTER Guide, Part 1, Sections 1.8-1.10: Application Process & Documents (30 min)

3. MASTER Guide, Part 1, Sections 1.11-1.13: Technical & Timeline (20 min)

4. MASTER Guide, Part 1, Sections 1.17-1.19: Common Issues & FAQs (15 min)

**Then for Detailed Implementation:**

Refer back to MASTER Part 1 for each step as you prepare documents

Use Section 1.10 (Document Checklist) as your daily tracker

Use Section 1.8 (Step-by-Step Process) as your playbook

**Timeline:** Allow 16 weeks minimum from application to approval

---

## For FBL Application Process

**Read in This Order:**

1. MASTER Guide, Part 2: FBL Overview (10 min)

2. PERMIT_02 Detailed Guide, Section 1-2: Legal Framework & Eligibility (15 min)

3. PERMIT_02 Detailed Guide, Section 3: Step-by-Step Application (45 min)

4. PERMIT_02 Detailed Guide, Sections 4-6: Forms, Checklist & Timeline (30 min)

**Then for Detailed Implementation:**

Use PERMIT_02 Section 3 as your step-by-step implementation guide

Use Section 8 Quick Checklist as your daily task list

Refer to Section 5 for common issues as you encounter them

**Timeline:** Allow 8-12 weeks from company registration to FBL approval

**Note:** FBL cannot start until after BOI approval (or approximately Month 5-6 of project)

---

## For EIA Process

**Read in This Order:**

1. MASTER Guide, Part 8: EIA Overview (20 min)

2. PERMIT_03 Detailed Guide, Section 1: Legal Framework (15 min)

3. PERMIT_03 Detailed Guide, Section 2: Full EIA Process (60 min) - This is crucial

4. PERMIT_03 Detailed Guide, Sections 4-6: Costs, Parameters & Common Issues (30 min)

**Then for Detailed Implementation:**

Start with PERMIT_03 Section 1 to confirm EIA requirement

Engage consultant and use PERMIT_03 Section 2 to brief them

Use PERMIT_03 Section 3 (Costs) for budget planning

Refer to Section 5 (Common Issues) during EIA development

**Timeline:** Allow 6-8 months from EIA screening to final approval

**Critical:** Start EIA work in parallel with BOI application (Month 1-2) to avoid timeline delays

---

## For Construction & Infrastructure Permits

**Permits Covered in MASTER Guide:**

Part 3: Land, Building & Construction (Sections 3.1-3.9)

Part 4: Electrical & Power (Sections 4.1-4.5)

Part 5: Water & Environmental (Sections 5.1-5.5)

**Reading Sequence:**

1. Applicable section overview (5-10 min)

2. Application process for your specific permit (10-20 min)

3. Document checklist (5 min)

4. Timeline and cost information (5 min)

**Implementation Strategy:**

Read permits in order: Building → Electrical → Water

Coordinate with design engineers (architectural, MEP, structural)

Ensure designs finalized before permit applications

Allow parallel processing (electrical and water permits can be applied simultaneously)

---

## For Operations & Compliance

**Covered in MASTER Guide:**

Part 10: Compliance, Reporting & Annual Obligations (Sections 10.1-10.4)

Part 1, Section 1.16: BOI Reporting & Compliance

**Key Documents to Maintain:**

BOI documents and annual reports (throughout tax holiday + 3 years after)

Environmental monitoring results (5-7 years)

Financial records (7 years per Thai law)

Employee work permits and training records (2-5 years)

**Annual Calendar (Post-Opening):**

Q1: BOI annual report due

Q2: Environmental monitoring reports due

Q3: Work permit renewals due

Q4: Tax compliance and audits

---

# COST SUMMARY BY PERMIT

## Fixed Government Fees

## Professional Services Costs

## Monthly Ongoing Costs (Post-Opening)

---

# FREQUENTLY ASKED QUESTIONS

## Q: Can I start construction before BOI approval?

**A:** No. While BOI approval is not technically a construction permit, many other permits (FBL, work permits) require BOI approval. More importantly, without BOI approval, you lose valuable tax incentives and utility connection priority. Recommended: Wait for BOI approval before construction starts (or at minimum, before significant expenditure).

## Q: Can I start building permit applications before EIA approval?

**A:** No. EIA approval is mandatory prerequisite to building permit in Thailand. You can prepare designs in parallel with EIA, but building permit application cannot be formally submitted until EIA is approved.

## Q: How long is the entire permitting process?

**A:** Minimum 24 months from first step to operations. Typical: 28-32 months. With delays: 36+ months. Critical path: EIA approval (6-8 mo) → Building permit (6-10 weeks) → Construction (12-18 mo).

## Q: What's the difference between 8.2.1.1 and 8.2.1.2 BOI categories?

**A:** Category 8.2.1.1 is for data centers serving only the investor's internal business. Category 8.2.1.2 is for commercial colocation/hosting for external customers. 8.2.1.2 receives longer tax holidays and more benefits, but requires FBL and stricter environmental compliance.

## Q: Do I need FBL if I have BOI approval?

**A:** Depends on foreign ownership and business model. If >50% foreign owned AND providing colocation services to external customers, yes FBL required. If purely internal use or Thai-owned, may not need FBL. Consult DBD early.

## Q: What if my project changes after BOI approval?

**A:** Capacity changes ±10% can be handled with BOI amendment (THB 2,000-5,000 fee). Larger changes or location/technology changes may require new application. Avoid major changes; finalize design before BOI application.

## Q: Who pays for environmental mitigation?

**A:** The developer/operator. All mitigation measures become conditions of operation. Costs are typically included in project budget (1-5% of construction cost for environmental systems).

## Q: What happens if I don't comply with EIA conditions?

**A:** ONEP can impose fines (THB 100K-500K+), require remediation, suspend permits, or escalate to criminal prosecution. Significant violations can result in project closure. Compliance is critical.

## Q: Can I hire a local consultant to manage permits?

**A:** Highly recommended. Local consultants understand Thai bureaucracy, have relationships with government agencies, and can often expedite processes. Cost: THB 100,000-200,000 for full permitting support.

---

# PROJECT MANAGEMENT CHECKLIST

## Pre-Project (Month -1-0)

[ ] Confirm BOI category eligibility (8.2.1.1 vs 8.2.1.2)

[ ] Confirm FBL requirement with DBD

[ ] Assess site environmental sensitivity

[ ] Estimate project capacity and timeline

[ ] Identify team and consultants needed

[ ] Prepare preliminary budget

## Month 1-2: Foundation

[ ] Incorporate Thai company

[ ] Obtain Tax ID

[ ] Begin BOI document preparation

[ ] Commission Phase 1 environmental site assessment

[ ] Engage EIA consultant

[ ] Submit EIA screening request

## Month 2-4: Applications

[ ] Complete and submit BOI application

[ ] Finalize land acquisition/lease

[ ] Begin FBL document preparation (in parallel)

[ ] Continue EIA study (TOR phase)

## Month 4-8: Approvals

[ ] Pursue BOI approval (expected Month 4-8)

[ ] EIA TOR approval (expected Month 6-8)

[ ] Begin FBL application (after BOI approval)

[ ] Finalize architectural designs

[ ] Commence EIA field studies

## Month 6-10: Pre-Construction

[ ] EIA completion and ONEP approval (expected Month 8-9)

[ ] Receive BOI certificate (expected Month 8)

[ ] Receive FBL approval (expected Month 9)

[ ] Submit building permit application

[ ] Secure construction contractor

[ ] Obtain construction license

## Month 10-14: Infrastructure Permits

[ ] Electrical design approval

[ ] Power utility connection request

[ ] Water connection request

[ ] Wastewater permit application

[ ] Generator license

[ ] Telecom coordination (if applicable)

[ ] Work permit applications for key foreign staff

## Month 14-28: Construction

[ ] Conduct monthly environmental monitoring

[ ] Respond to environmental monitoring data

[ ] Complete building construction

[ ] Install MEP systems

[ ] Install IT infrastructure

[ ] Commission systems

## Month 28-30: Pre-Operations

[ ] Request final fire safety inspection

[ ] Request final electrical inspection

[ ] Request occupancy permit

[ ] Activate utilities (electricity, water, telecom)

[ ] Staff training and readiness

[ ] Final system testing

## Month 30+: Operations

[ ] Begin operations

[ ] Establish environmental monitoring schedule

[ ] Set up BOI annual reporting process

[ ] Schedule work permit renewals

[ ] Maintain all environmental permits and compliance

[ ] Conduct annual facility inspections

---

# WHEN TO CONTACT GOVERNMENT AGENCIES

## Board of Investment (BOI)

**Month 1:** Preliminary consultation on category and requirements

**Month 2:** Submit BOI application

**Month 8-12:** Annual BOI compliance reporting

## ONEP (Environmental)

**Month 1-2:** EIA screening request

**Month 5:** Submit TOR for approval

**Month 11-12:** Submit draft EIA report

**Month 13-18:** Support public consultation

**Month 18-24:** Respond to ONEP comments

**Year 2+:** Annual environmental monitoring reports

## Department of Business Development (DBD)

**Month 1:** Confirm FBL requirement

**Month 5-6:** FBL application (after BOI approval)

**Month 12+:** Annual FBL renewals

## Local Authority (Municipality)

**Month 8-9:** Submit building permit application

**Month 10-11:** Final building permit and construction license

**Month 28-29:** Occupancy permit

## Electricity Authority (PEA/MEA)

**Month 6-7:** Power connection request

**Month 28-29:** Final connection and activation

---

# FINAL RECOMMENDATIONS

## Before You Start

1. **Clarify your business model** - Internal use (8.2.1.1) vs. Commercial colocation (8.2.1.2)

2. **Engage local expertise** - Hire experienced BOI and FBL consultant (ROI is positive)

3. **Get early ONEP consultation** - Confirm EIA requirement before major site commitment

4. **Plan for 24-32 months** - Permitting timeline is much longer than construction budget implies

5. **Budget conservatively** - Add 20-30% contingency for permit delays and environmental requirements

## Project Governance

1. **Assign permit manager** - Single person accountable for permit timeline and compliance

2. **Create critical path schedule** - Identify which permits determine project timeline

3. **Build in 10-20% buffer** - Permits often take longer than estimated

4. **Monthly compliance review** - Track actual vs. planned progress on all permits

5. **Escalation procedure** - Define who approves responses to government requests

## Common Pitfalls to Avoid

1. **Starting construction before EIA approval** - Illegal and results in project stoppage

2. **Underestimating environmental sensitivity** - Early assessment critical

3. **Incomplete permit applications** - Causes 2-4 week delays per missing document

4. **Not engaging professional consultants** - False economy; consultants often save time and money

5. **Changing project design after BOI approval** - Causes major delays and rework

6. **Ignoring compliance requirements after approval** - Creates legal and operational risk

---

**NEXT STEP:** Begin with reading the MASTER Guide, then dive into detailed guides for your specific permits.