# FOREIGN BUSINESS LICENSE (FBL) - DETAILED IMPLEMENTATION GUIDE

# Thailand Data Center Operations

---

# QUICK REFERENCE

---

# SECTION 1: LEGAL FRAMEWORK

## When FBL is Required

**Foreign Business Act Categories:**

**Schedule 1 (Completely Restricted):**

These businesses are completely prohibited for foreign operation

Data centers are NOT on this list

**Schedule 2 (Thai Majority Required):**

Foreign ownership limited to maximum 49%

Data center operations are NOT on this list

**Schedule 3 (Foreign License Required):**

Foreign companies can operate WITH Foreign Business License

**Data center colocation/hosting for external parties = Schedule 3**

**Data center internal use may fall outside scope if purely for own operations**

## Practical Test for Data Center

**FBL Required if:**

Data center offers colocation services to third parties (Category 8.2.1.2)

Data center offers managed hosting services

Data center offers bandwidth/connectivity services

Foreign ownership >50%

**FBL Likely NOT Required if:**

Data center for internal use only (Category 8.2.1.1)

Pure infrastructure investor with Thai management company

Facility operation contracted to Thai company

**Recommendation:** Consult with DBD early if uncertain

---

# SECTION 2: DETAILED ELIGIBILITY REQUIREMENTS

## 2.1 Company Structure Requirements

**For Foreign Company (Incorporated Outside Thailand):**

Must establish Thai subsidiary (Thai legal entity)

Cannot directly operate as foreign entity

Thai company is the FBL applicant

Foreign company is the investor/shareholder

**For Thai Company with Foreign Investor:**

Thai company incorporated per Thai law

Foreign investor >50% ownership

Management structure determines operational control

## 2.2 Capital Requirements

**Minimum Registered Capital:**

THB 2,000,000 for data center operations

Capital must be paid-up (actually deposited to company account)

For foreign company: Must remain in Thai bank account for minimum 3 months before FBL approval

**Proof of Capital (Required Documents):**

1. Bank statement showing capital deposit

2. Bank certification letter

3. Deposit receipt or fund transfer proof

4. Board resolution authorizing capital contribution

5. Shareholder agreement showing capital commitment

**Common Capital Issues:**

Capital deposit in foreign currency not accepted—must be THB

Temporary/short-term loans do not count as capital

Guarantee letters insufficient; must be actual deposit

Capital must remain in account until FBL approval (then can be used)

## 2.3 Governance and Management

**Thai Directors Requirement:**

Minimum 1 Thai national director required (of 3-person board minimum)

Director must be Thai national (ID card holder)

Can hire professional Thai director if non-Thai founders

Professional directors typically charge THB 10,000-20,000 per year

**Authorized Signatories:**

At least one person must be authorized to sign FBL applications

Typically Thai director or Thai manager

Board resolution must specify signatory authority

## 2.4 Shareholder/Ownership Documentation

**Foreign Investor Identification:**

Valid passport (photo page and signature)

Home country tax identification (ID number or tax certificate)

Certificate of no criminal record (apostilled)

Personal financial statements (if significant investor)

**Corporate Investor Documentation:**

Company incorporation certificate (apostilled)

Good standing certificate (apostilled)

Board resolution authorizing Thai investment (apostilled)

Financial statements of parent company (last 2 years)

Tax documentation in home country

**Ownership Structure Verification:**

Shareholder register showing all owners

Share certificates or cap table

Proof of ownership (payment receipts, transfer documents)

Org chart showing management structure

---

# SECTION 3: STEP-BY-STEP APPLICATION PROCESS

## Phase 1: Pre-Application Preparation (Weeks 1-2)

**Step 1: Confirm Business Classification**

Contact DBD to confirm FBL requirement for your specific data center business model

Email: [inquiry@dbd.go.th](mailto:inquiry@dbd.go.th)

Phone: 0-2547-3000

Provide business description, services offered, ownership structure

Receive written confirmation of FBL requirement (or exemption if applicable)

**Step 2: Establish Thai Company (if not already incorporated)**

Identify Thai incorporation service provider

Provide company name (must be unique, not similar to existing companies)

Specify Thai directors and shareholders

Register with DBD

Receive Certificate of Registration (within 1-2 days)

Obtain company seal and tax ID

**Step 3: Organize Governance Meetings**

Initial shareholders meeting

Elect board of directors (at least 1 Thai national)

Appoint authorized signatory

Approve FBL application

Prepare meeting minutes and board resolutions

## Phase 2: Documentation Preparation (Weeks 3-4)

**Step 4: Prepare Company Documents**

[ ] Certificate of Business Registration (from DBD)

[ ] Articles of Association (from DBD registration)

[ ] Board of Directors resolution:

- Approving FBL application

- Authorizing signatory

- Dated and signed by at least 2 directors

- Affixed with company seal

[ ] Shareholder register

[ ] Company bank account details

[ ] Organizational chart

**Step 5: Prepare Foreign Investor Documents**

[ ] Valid passport copy (if individual investor):

- Photo and signature pages

- Must be readable and current

[ ] Certificate of no criminal record (individual):

- From home country law enforcement

- Must be apostilled (international certification)

- Not older than 6 months when submitted

- English translation (if not in English)

[ ] Tax identification document from home country:

- Tax ID number

- Tax registration certificate

- Most recent tax return (if available)

[ ] Financial capacity documentation (if significant individual investor):

- Bank statements (last 3 months)

- Financial statements

- Proof of income/employment

- Investment commitment letter

**Step 6: Prepare Capital Proof Documents**

[ ] Bank statement showing THB 2,000,000 deposit (original or certified copy)

[ ] Bank certification letter (on bank letterhead):

- Confirming fund deposit

- Confirming account holder (company name)

- Confirming account balance

- Confirming deposit date

[ ] Fund transfer/deposit receipt

[ ] Board resolution approving capital contribution

[ ] Shareholder meeting minutes approving capital

**Step 7: Prepare Business Plan (Thai Language)**

Executive summary (1 page)

Business description (2-3 pages):

- Data center location (address)

- Services offered (colocation, hosting, bandwidth, etc.)

- Target customers (enterprises, ISPs, etc.)

- Monthly/annual revenue projections

- Operating personnel count

Service specifications (2-3 pages):

- Data center capacity (MW, rack units)

- Service uptime guarantee (SLA)

- Security measures

- Environmental controls

- Backup and disaster recovery

Operational procedures (1-2 pages):

- Customer on-boarding process

- Billing procedures

- Service level maintenance

- Support team structure

Financial projections (1 year minimum)

Thai office location details (address, size)

## Phase 3: Document Translation and Certification (Weeks 5-6)

**Step 8: Professional Translation of Foreign Documents**

All foreign documents must be translated to Thai

Use certified translator or translation service

Typical cost: THB 50-200 per page

Translator must certify accuracy

Required documents:

- Passport

- Certificate of no criminal record

- Corporate incorporation documents

- Tax documents

- Financial statements

**Step 9: Apostille and Legalization (if required)**

Documents from foreign countries require apostille

Apostille process:

1. Obtain from issuing authority in home country

2. Submitted with original document

3. Certified copy of apostille document

Documents typically requiring apostille:

- Certificate of no criminal record (CRITICAL)

- Corporate incorporation documents

- Board resolutions

- Good standing certificates

- Tax documents

Common sources for apostille:

- Secretary of State (USA)

- Ministry of Justice (various countries)

- County offices

- International notaries

Timeline: 2-6 weeks to obtain from home country

**Plan ahead for this step**

## Phase 4: FBL Application Submission (Week 7)

**Step 10: Complete FBL Application Form**

Form name: **Form P.13** (Application for Permission to Engage in Foreign Business)

Available at: www.dbd.go.th (download or obtain at office)

Sections to complete:

1. Company name and registration number

2. Company address

3. Type of foreign business activity (select from lists provided)

4. Name and address of foreign investors (each)

5. Nationality and passport number of foreign investors

6. Capital amount and breakdown

7. Authorized signatories

8. Thai management personnel

9. Attached documents checklist

10. Signature of authorized person and company seal

**Step 11: Prepare FBL Application Package**

Original or certified copy of Form P.13

All required documents in proper order:

- Company registration and governance documents

- Investor identification documents (passports, translations)

- Criminal record certificates (apostilled, translated)

- Capital proof documents

- Business plan (Thai language)

- Land/office lease agreement

- Management team identification documents

**Step 12: Submit FBL Application**

**Submission Method 1: In Person**

- Go to DBD office (555 Rama IV Rd, Bangkok, or regional office)

- Submit to Foreign Business Division

- Bring original documents + 1 copy

- Pay fee (THB 5,000)

- Receive receipt and tracking number

- Timeline to submission: 1 day

**Submission Method 2: By Mail**

- Send original documents with certified copies

- Include cover letter with contact information

- Registered mail with tracking

- Include check for THB 5,000 (or bank transfer)

- Timeline to submission: 3-5 days

**Submission Method 3: Through Agent/Consultant**

- Hire DBD-accredited FBL consultant

- Consultant submits on your behalf (with power of attorney)

- Consultant handles correspondence with DBD

- Cost: THB 50,000-100,000

- Timeline to submission: 2-4 days

**Document Submission Checklist:**

## Phase 5: DBD Review (Weeks 8-10)

**Step 13: Initial Completeness Review**

DBD reviews submitted documents

Timeline: 3-5 business days

Possible outcomes:

- **Complete:** Proceeds to substantive review

- **Incomplete:** Requests additional documents (typically 5-7 business day deadline to resubmit)

If incomplete, resubmit missing documents immediately

- Use same reference number

- Include cover letter referencing original submission

**Step 14: Substantive Review**

DBD examines each document for accuracy and compliance

Activities:

- Verify capital deposit with bank (may contact bank directly)

- Verify no criminal record

- Assess business plan viability

- Verify Thai director credentials

- Check company registration validity

- Confirm foreign investor identification

Timeline: 1-2 weeks

Possible outcomes:

- **Approved:** Certificate issued

- **Requests Clarification:** Asks for additional information, explanation, or modifications

- **Rejected:** Denies FBL application (provide reasons)

**Step 15: Respond to Information Requests (if any)**

DBD may ask for:

- Clarification on business plan

- Additional financial documentation

- Proof of management experience

- Verification of investor identity

- Revised business plan with modifications

Response deadline: Typically 7-10 business days

Submit response immediately to avoid timeline slippage

Use same reference number and cover letter

## Phase 6: Approval and Issuance (Week 11)

**Step 16: Receive FBL Certificate**

Upon approval, DBD issues:

- Foreign Business License Certificate (Usufruct/Operation License)

- Document indicating approved foreign business activity

- List of foreign investors approved for the license

- License number and issuance date

- Validity period (typically 1 year from issuance)

Document can be:

- Picked up in person at DBD office (1-2 days processing)

- Mailed to applicant address (3-5 days)

- Obtained through agent (if agent submitted)

**Step 17: Annual Renewal Registration**

**Timeline:** FBL must be renewed annually before expiration date

**Timeline for Renewal:** Submit 30-60 days before expiration

**Renewal Process (simpler than initial):**

1. Submit Form P.14 (Renewal Application)

2. Updated company registration certificate

3. Updated business plan (if significant changes)

4. Capital proof (if capital increased, decreased, or changed)

5. Updated list of foreign investors (if ownership changed)

6. Renewal fee: THB 1,000

7. Processing time: 2-3 weeks

---

# SECTION 4: REQUIRED FORMS AND DOCUMENTS DETAILS

## Form P.13 - Application for Foreign Business License

**Where to Obtain:**

DBD website: www.dbd.go.th/forms/

DBD office in person

Email request to [contact@dbd.go.th](mailto:contact@dbd.go.th)

Thailand's online portal (if available)

**Form Sections (Line by Line Guidance):**

**Section 1: Applicant Information**

Company name: Enter exact name from registration certificate

Company registration number: From DBD certificate

Registered office address: Full address including province and postal code

Business type: Select "Data Center Services" or relevant category

Telephone number: Company business phone

Email: Company contact email

**Section 2: Foreign Business Activity Description**

Describe business in detail:

- "Colocation and hosting services for data center customers"

- "Provision of rack space, power, cooling, and network connectivity to third-party users"

- "Data center facility management and operations"

Specify services (select all applicable):

- [ ] Colocation services

- [ ] Managed hosting

- [ ] Cloud infrastructure

- [ ] Network/bandwidth services

- [ ] Disaster recovery services

- [ ] Other (specify): ___________

**Section 3: Foreign Investors**

List all foreign investors (shareholders >10% ownership or significant investors)

For each:

- Name

- Nationality

- Passport number

- Address in home country

- Ownership percentage

- Role (investor, manager, etc.)

- Signature or thumbprint (if in person)

**Section 4: Authorized Representatives**

Name of person authorized to operate the business

Position in company

Thai national (required) or foreign national

Identification number

Contact information

**Section 5: Capital Information**

Total registered capital: THB 2,000,000

Paid-up capital: THB 2,000,000 (must be paid by submission)

Currency: Thai Baht

Source of capital (foreign or domestic)

**Section 6: Attachments Checklist**

Mark which documents are attached:

- [ ] Company registration certificate

- [ ] Articles of Association

- [ ] Board resolutions

- [ ] Investor identification documents

- [ ] Capital proof

- [ ] Business plan

- [ ] Land/lease agreement

- [ ] Other: ____________

**Section 7: Declaration and Signature**

"I hereby certify that the information provided is true and accurate"

Signature of authorized person

Company seal

Date

## Other Critical Documents

**Business Plan (Thai Language) - Template Structure:**

```

I. บทสรุปผู้บริหาร (Executive Summary) - 1 page

- กิจการ (Business type): Data Center Operations

- ที่ตั้ง (Location): [Address]

- ลักษณะบริการ (Services): [Description]

- เป้าหมาย (Objectives): Growth, customer acquisition

- ระยะเวลา (Timeline): 5-10 years

II. รายละเอียดธุรกิจ (Business Description) - 2-3 pages

- ประวัติความเป็นมา (Background)

- โครงสร้างอาคาร (Building structure)

- ความจุ (Capacity): [MW, RUs]

- ระบบหลัก (Systems): Power, cooling, security

- ระยะเวลาดำเนินการ (Operating hours): 24/7

III. บริการและผลิตภัณฑ์ (Services and Products) - 2-3 pages

- บริการโคโลเคชัน (Colocation services)

- บริการจัดการ (Managed services)

- บริการสนับสนุน (Support services)

- ราคา (Pricing)

- SLA (Service Level Agreement)

IV. กลุ่มลูกค้าเป้าหมาย (Target Market) - 1-2 pages

- บริษัทเทคโนโลยี (Tech companies)

- ผู้ให้บริการอินเทอร์เน็ต (ISPs)

- บริษัทการเงิน (Financial companies)

- หน่วยงานราชการ (Government agencies)

- ธุรกิจท่องเที่ยว (Tourism businesses)

V. การดำเนินการและการจัดการ (Operations) - 2 pages

- ทีมจัดการ (Management team)

- พนักงาน (Staff): [Number and positions]

- ขั้นตอนการให้บริการ (Service procedures)

- ระบบการเรียกเก็บ (Billing system)

- ติดต่อลูกค้า (Customer communication)

VI. การเงิน (Financial Projections) - 1-2 pages

- การลงทุน (Investment): THB [Amount]

- รายได้คาดหวัง (Revenue): THB [Amount/year]

- ต้นทุน (Costs): [Operational expenses]

- กำไร (Profit margins): [Expected %]

VII. เอกสารแนบ (Attachments)

- สำเนาสัญญาเช่า (Lease agreement)

- แผนผังอาคาร (Building plan)

- ใบรับรองการสอบบัญชี (Financial statements)

```

**Business Plan Tips:**

Use professional Thai translator for translation

Include specific numbers (revenue projections, staff count, etc.)

Describe operational procedures in detail

Show understanding of Thai market

Emphasize job creation and economic contribution

Keep realistic and achievable (overly optimistic plans are rejected)

---

# SECTION 5: COMMON ISSUES AND SOLUTIONS

## Issue 1: Criminal Record Certificate Expired

**Problem:** Certificate of no criminal record is >6 months old

**Prevention:**

Obtain certificate within 2-3 months before FBL submission

Order well in advance from home country authorities

**Solution if Already Submitted:**

Contact home country authorities for new certificate (1-4 weeks)

Resubmit to DBD with updated certificate

Timeline impact: 4-6 week delay

## Issue 2: Capital Not Actually Deposited

**Problem:** Shows capital on paper but funds never actually transferred

**DBD Verification:**

DBD often contacts bank to confirm deposit

Bank statement must show actual funds, not just line of credit

Account must show funds available/not withdrawn

**Prevention:**

Actually deposit funds to bank account (not a loan)

Keep funds in account through approval (don't withdraw)

Provide bank certification letter confirming deposit

**If Already an Issue:**

Deposit funds immediately to account

Obtain new bank statement

Request bank certification letter

Explain delay to DBD

Resubmit with updated documents

## Issue 3: Insufficient Business Plan

**Problem:** Business plan is too vague or doesn't address DBD concerns

**Common Deficiencies:**

No detailed operational procedures

Unrealistic financial projections

Unclear target market

No description of Thai staff plans

Missing location/address details

**Solution:**

Review DBD feedback carefully

Rewrite business plan addressing specific concerns

Add more detail and specificity

Include organizational chart with positions

Provide staff hiring plan (Thai workforce)

Update financial projections if needed

Resubmit within requested timeline (typically 7-10 days)

**Best Practices:**

Have Thai consultant review plan before first submission

Use specific numbers, not vague percentages

Demonstrate knowledge of Thai market and regulations

Emphasize Thai staff employment and training

## Issue 4: Unauthorized Signatory

**Problem:** Document signed by person not authorized (wrong director, non-authorized person)

**Prevention:**

Board resolution must specifically authorize who can sign FBL documents

Keep signed and sealed board resolution with signatory authorization

Verify signatory identity matches board resolution before signing

Use same signatory for all documents if possible

**Solution if Occurred:**

Obtain new board resolution authorizing correct person

Have correct authorized person re-sign all documents

Resubmit with explanation letter

1-2 week delay

## Issue 5: Foreign Investor Not Clearly Identified

**Problem:** Unclear who the foreign investor is, ownership percentages, or beneficial ownership

**Prevention:**

Provide shareholder register showing all owners

Include cap table with ownership percentages

Identify all foreign shareholders >10%

Provide personal identification for each foreign investor

If corporate investor, identify ultimate beneficial owners if possible

Include organizational/ownership chart

**Solution:**

Clarify ownership structure with detailed shareholder register

Provide identification for all foreign parties

Provide cap table showing ownership percentages

Resubmit within 7-10 days

## Issue 6: Business Activity Not Properly Described

**Problem:** DBD unclear if business actually requires FBL or what classification applies

**Prevention:**

Before applying, confirm with DBD that FBL is required

Get written confirmation of business classification

In Form P.13, specifically describe colocation/hosting for third parties

Make clear that it's not purely internal-use data center

**Solution:**

Clearly restate business model (colocation for external customers)

Emphasize revenue-generating aspect

Provide customer contract examples or LOI

Describe service offerings in detail

Resubmit with clarification letter

---

# SECTION 6: TIMELINE SUMMARY

**Timeline Acceleration Options:**

Expedite apostille process in home country (rush service often available)

Use FBL consultant (can compress timeline by 1-2 weeks through experience and relationships)

Submit with perfect documents (eliminates information request phase)

**Timeline Delays:**

Incomplete apostille documentation: +2-4 weeks

Information requests from DBD: +1-2 weeks each round

Criminal record certificate issues: +4-6 weeks

Capital verification problems: +2-3 weeks

---

# SECTION 7: COSTS BREAKDOWN

---

# SECTION 8: ANNUAL RENEWAL PROCESS

## Renewal Requirements

**Form Required:** Form P.14 (Renewal Application)

**Documents to Submit:**

1. Form P.14 (signed and sealed)

2. Current company registration certificate

3. Updated business plan (if significant changes)

4. Updated shareholder register (if ownership changed)

5. Capital proof (if capital changed)

6. List of foreign investors (if changed)

7. Renewal fee (THB 1,000)

## Renewal Timeline

**Submission Window:** 30-60 days before license expiration

**Processing Time:** 2-3 weeks

**Total:** Renewal can be completed in 3-4 weeks if submitted on time

## What Changes Require Amended License

**Minor Changes (included in renewal):**

Foreign investor name changes

Foreign investor address changes

Thai staff changes

Telephone/email changes

Business plan updates

**Major Changes (require new application or amendment):**

Change in primary foreign investors (>10% ownership change)

Change in business type or services offered significantly

Significant increase/decrease in capital

Change in Thai director

Change in registered location (different province)

For major changes, may need to apply for amended license (Form P.14 with explanation and supporting docs).

---

# SECTION 9: CONTACTS AND RESOURCES

## Department of Business Development (DBD)

**Head Office:**

Address: 119 Moo 3, Rama IX Rd, Bangkapi, Bangkok 10310

Phone: 0-2547-3000

Fax: 0-2547-3100

Email: [info@dbd.go.th](mailto:info@dbd.go.th)

Website: www.dbd.go.th

Hours: Monday-Friday, 8:30 AM - 4:30 PM

**Foreign Business Division:**

Handles FBL applications

May be specific department within DBD

Same phone number, ask for Foreign Business Division

**Regional DBD Offices:**

Bangkok, Chiang Mai, Khon Kaen, Rayong, Phuket, Hat Yai

## Recommended Process Timeline

1. **Week 1:** Contact DBD to confirm FBL requirement

2. **Weeks 2-3:** Establish Thai company (if needed)

3. **Weeks 4-5:** Begin document gathering and translation

4. **Weeks 6-8:** Obtain apostilles from home country

5. **Week 9:** Submit FBL application

6. **Weeks 10-12:** DBD review and approval

7. **Week 12:** Receive FBL certificate

---

# QUICK CHECKLIST - FBL APPLICATION

## Pre-Submission Verification

[ ] DBD confirmed FBL requirement in writing

[ ] Thai company incorporated and registered with DBD

[ ] Thai Tax ID obtained

[ ] Board of Directors appointed (includes Thai national)

[ ] THB 2,000,000 deposited to company bank account

[ ] Bank certification letter obtained

[ ] All foreign documents translated to Thai

[ ] All foreign documents apostilled (where required)

[ ] Foreign investor criminal records obtained and apostilled

[ ] Business plan written in Thai (5-10 pages)

[ ] Form P.13 completed in full

[ ] All documents organized in proper order

[ ] Original + 1 copy prepared for all documents

[ ] Company seal obtained

[ ] Form P.13 signed and sealed by authorized person

[ ] Cover letter prepared (if submitting by mail)

## Documents to Bring/Submit

[ ] Form P.13 (original + copy)

[ ] Company registration certificate (original + copy)

[ ] Articles of Association (copy)

[ ] Board resolutions (original + copy)

[ ] Shareholder register (copy)

[ ] Passport copies with translations (original + copy)

[ ] Criminal record certificates with apostilles and translations (original + copy)

[ ] Corporate docs (if corporate investor) with apostilles and translations

[ ] Bank statement showing capital deposit (original + copy)

[ ] Bank certification letter (original + copy)

[ ] Business plan in Thai (copy)

[ ] Proof of office/location (lease agreement, copy)

[ ] Application fee (THB 5,000)

---

# FINAL NOTES

1. **Early Consultation:** Always consult with DBD early to confirm FBL requirement—don't assume

2. **Apostille Critical:** The criminal record apostille is often the longest lead item—order immediately

3. **Professional Help:** Consider hiring FBL consultant to navigate process—cost (~THB 75,000) is often worth it

4. **Keep Original Documents:** Don't submit original passport or certificate of no criminal record—keep copies and certified copies

5. **Thai Language:** All foreign documents must be officially translated to Thai—use professional translators

6. **Timeline Planning:** 8-12 weeks is normal—plan accordingly in project schedule