# COMPLETE THAILAND DATA CENTER PERMITTING DOCUMENTATION

# Executive Summary & Document Map

**Prepared for:** GFL Cut-In Project (CHN1A)

**As of:** June 30, 2026

**Total Documentation Package:** 5 Comprehensive Guides

---

# DOCUMENT PACKAGE OVERVIEW

You now have a complete permitting reference library with **5 interconnected documents**:

## TIER 1: MASTER REFERENCE (For Understanding Complete Landscape)

**File:** `THAILAND_DATA_CENTER_COMPLETE_PERMITTING_GUIDE.md`

**Size:** 50+ pages

**Scope:** All 9 major permit categories

**Use Case:** Complete reference guide, regulatory framework, official contacts

**Reading Time:** 2-3 hours for full review

**Contents:**

9 Major permit categories (BOI, FBL, Land, Building, Electrical, Water, Telecom, Labor, Customs)

20+ individual permits

Complete government fees breakdown

Official agency contacts

Legal framework and Thai government notifications

Best practices and common pitfalls

---

## TIER 2: DETAILED IMPLEMENTATION GUIDES (For Deep Dives)

**File 1:** `PERMIT_02_FOREIGN_BUSINESS_LICENSE_DETAILED.md`

**Size:** 20+ pages

**Purpose:** Step-by-step FBL application guide

**Reading Time:** 1-2 hours

**Best For:** Foreign investors needing FBL approval

**File 2:** `PERMIT_03_ENVIRONMENTAL_IMPACT_ASSESSMENT_DETAILED.md`

**Size:** 25+ pages

**Purpose:** Complete EIA process walkthrough

**Reading Time:** 1.5-2 hours

**Best For:** Understanding environmental approval pathway (6-8 month process)

---

## TIER 3: PROJECT-SPECIFIC ANALYSIS (For Your CHN1A Project)

**File:** `CHN1A_PROJECT_PERMIT_ANALYSIS.md`

**Size:** 30+ pages

**Purpose:** Maps your actual permits to comprehensive guides + risk assessment

**Reading Time:** 1-2 hours

**Best For:** Understanding your specific project timeline and gaps

**Contents:**

Analysis of your 14 permits

Comparison to guide recommendations

Identification of 7 missing permits to verify

Risk assessment matrix

Recommendations by priority (Immediate, Second, Third)

Contingency strategies

Cost estimation for missing items

---

## TIER 4: NAVIGATION & INDEX (For Finding What You Need)

**File:** `00_PERMITTING_GUIDE_NAVIGATION.md`

**Size:** 15+ pages

**Purpose:** How to use the entire documentation package

**Reading Time:** 30 minutes

**Best For:** First document to read (orientation)

**Contents:**

Quick start guide (15 min, 1 hour, deep dive options)

Critical permits by project phase

Permit dependency map

Critical path analysis

Key contacts quick reference

Document-by-document reading guide

---

# HOW TO USE THIS DOCUMENTATION PACKAGE

## Scenario 1: "I have 15 minutes - what do I need to know?"

**Read:**

1. This summary (5 min)

2. Navigation Guide - "Quick Start" section (10 min)

**Outcome:** Understanding of permit sequence and critical timeline

---

## Scenario 2: "I'm managing permits - where do I start?"

**Read in this order:**

1. Navigation Guide - full (20 min)

2. CHN1A Project Analysis - Sections 1-3 (30 min)

3. Master Guide - relevant sections as needed (30+ min)

**Outcome:** Clear picture of what's required, what's at risk, what to do now

---

## Scenario 3: "I need to manage specific permit (e.g., EIA or FBL)"

**Read:**

1. Master Guide - relevant section overview (10 min)

2. Detailed Permit Guide (if available) - full document (1 hour)

3. Return to Master Guide - as reference during implementation

**Outcome:** Step-by-step instructions for completing that permit

---

## Scenario 4: "I'm a project executive - give me the situation report"

**Read:**

1. This summary (5 min)

2. CHN1A Project Analysis - Executive Summary + Sections 1, 4 (30 min)

3. Risk Assessment section (20 min)

4. Critical Actions section (10 min)

**Outcome:** Dashboard view of project health, risks, and decisions needed

---

# YOUR CHN1A PROJECT STATUS SNAPSHOT

## What's Tracked (14 Permits)

**Timeline:** April 2026 → January 27, 2027 (9 months)

**Current Date:** June 30, 2026 (Mid-project)

---

## What's MISSING (Needs Verification)

## Critical Risk Assessment

---

# CRITICAL ACTIONS - NEXT 30 DAYS (July 2026)

## IMMEDIATE (Do This Week)

1. **Confirm Missing Permits** 🔴

- Get BOI Promotion Certificate (or confirmation of approval)

- Get EIA Approval Certificate (or confirmation of exemption)

- Confirm FBL status (required? approved?)

- Document all three in project records

2. **Schedule Building Cert Pre-Inspection** 🔴

- Contact AHJ in early August

- Schedule pre-inspection of building (before Oct 14 submission)

- Identify potential defects early

- Budget: 1-2 weeks for corrections if issues found

3. **Lock Building Certificate Timeline** 🔴

- Confirm Aug 15 POA deadline realistic

- Confirm Oct 14 submission doable

- If timeline slipping: Escalate to decision-makers NOW

- Current plan: Oct submit → Jan 27 receive (3+ months)

## SECOND PRIORITY (Next 2 Weeks)

4. **Finalize Water/Wastewater Designs** 🟡

- All design docs ready by Aug 1 (buffer before Aug 9 submission)

- Coordinate with WHA feedback loop

- Confirm treatment systems capacity

- Budget for equipment: THB 1-3M (order by Aug 1)

5. **Establish Environmental Management** 🟡

- Get EIA Approval Certificate

- Document all mitigation measures

- Create 5-year monitoring/compliance budget (THB 250-500K)

- Assign environmental manager

6. **Identify Waste Disposal Contractors** 🟡

- Characterize waste streams (hazardous vs. non-hazardous)

- Contact 3-4 licensed contractors

- Reserve capacity (some have limits)

- Budget: THB 100-300K annually

## THIRD PRIORITY (By End of July)

7. **Confirm Foreign Staff Work Permits** 🟡

- List all foreign employees planned

- Initiate work permit documentation (1-2 weeks per employee)

- Submit by August if possible (parallel with other permits)

8. **Coordinate NBTC Telecom License** 🟡

- Clarify scope of "other licensing" (ISP? Gateway?)

- If complex telecom service: Get early confirmation of feasibility

- If simple walkie-talkie only: Proceed as scheduled

---

# DOCUMENT REFERENCE BY TOPIC

## For BOI Questions → Master Guide Part 1

Eligibility, incentives, application process, timeline, costs

Forms: TM.30, Power of Attorney

Authority: Board of Investment (www.boi.go.th)

Timeline: 16 weeks from application

## For FBL Questions → PERMIT_02 Detailed Guide (OR Master Guide Part 2)

Step-by-step application

Document checklist (20+ items)

Common issues and solutions

Authority: Department of Business Development (www.dbd.go.th)

Timeline: 8-12 weeks

## For EIA Questions → PERMIT_03 Detailed Guide (OR Master Guide Part 8)

Full EIA process (4 phases: Screening, TOR, Study, Approval)

Baseline monitoring requirements

Cost and timeline (6-8 months)

Authority: ONEP (www.onep.go.th)

## For Building Permits → Master Guide Part 3

Building permit application, fire safety, construction licensing

Land documentation requirements

Authority: AHJ (Local Authority)

Timeline: 6-10 weeks + 3+ months review

## For Electrical/Power → Master Guide Part 4

Electrical design, power utility connection, generator licensing

Dual-feed vs. single-feed decision

Authority: PEA/MEA, DEDE, Department of Labor

Timeline: 8-16 weeks for infrastructure

## For Water/Environmental → Master Guide Part 5

Water supply, wastewater discharge, environmental permits

Treatment system specifications

Authority: WHA/PWA, PCD, Department of Labor

Timeline: 6-10 weeks

## For Your Specific Project Issues → CHN1A_PROJECT_PERMIT_ANALYSIS.md

Your 14 permits analyzed individually

Missing permits identified

Risk assessment for your project

Recommendations prioritized by timeline

---

# GOVERNMENT AGENCY MASTER CONTACT LIST

---

# COST SUMMARY

## Government Fees (One-Time)

BOI Application: 5-10K

FBL Initial: 5K

Building Permits: 10-100K

EIA: 5-50K

Other permits: ~50-100K

**Total Government Fees: 75-265K THB**

## Professional Services (Project Duration)

Consultants & advisors: 1-2.5M THB

Engineering (included in construction): 5-10% of build

**Total Professional: 1-2.5M THB**

## Infrastructure (Long-term)

Power upgrades: 20-100M THB

Water systems: 2-5M THB

Environmental systems: 2-5M THB

Telecom infrastructure: 10-50M THB

**Total Infrastructure: 34-160M THB**

## Annual Ongoing (Post-Opening)

Utilities: 2-3M THB/month

Environmental monitoring: 50-100K THB/year

Compliance/reporting: 20-30K THB/year

Work permit renewals: 3,600/employee/year

Insurance: 2-10M THB/year

**Total Annual: 30-45M THB/year**

---

# KEY TIMELINE MILESTONES (Your Project)

```

Jun 30, 2026 (TODAY)

│

├─ JUL 2026 - CONFIRM MISSING PERMITS & ACCELERATE DESIGN

│  ├─ Verify BOI, EIA, FBL status

│  ├─ Schedule Building Cert pre-inspection

│  └─ Finalize water/wastewater designs

│

├─ AUG-SEP 2026 - INFRASTRUCTURE INSPECTIONS

│  ├─ Building pre-inspection (Aug)

│  ├─ Electrical/Fire safety inspections

│  ├─ Power, water, wastewater activations

│  └─ Generator/fuel systems ready

│

├─ OCT-DEC 2026 - FINAL PERMITS

│  ├─ Building Occupancy Certificate submission (Oct 14)

│  ├─ Operations Permit (IEAT 03/2) submission (Dec 23)

│  ├─ Final inspections & approvals

│  └─ Systems commissioning

│

└─ JAN 27, 2027 - OPERATIONS START

├─ Building Occupancy Certificate approval

├─ Business Operations Permit approval

├─ All utilities activated

└─ FACILITY OPERATIONAL ✅

```

**Total Timeline:** 7 months remaining (currently on track if no major slips)

---

# DECISION MATRIX - WHAT TO DO NOW

---

# FREQUENTLY ASKED QUESTIONS

**Q: Can I operate before all permits approved?**

A: No. Business Operations Permit (IEAT 03/2) is legally required before any operational activity. Operating without it = fines, criminal penalties, possible imprisonment.

**Q: What if Building Certificate slips to February 2027?**

A: Operations Permit automatically cannot be approved. Facility cannot legally operate. Revenue loss: ~10-50M THB/month depending on capacity. Start contingency planning now.

**Q: Is EIA really required?**

A: Confirm with ONEP screening. If >500 kW capacity or sensitive location: yes. Missing EIA approval can halt operations. Get documentation immediately.

**Q: How much buffer should I have for timelines?**

A: Minimum 20-30% buffer for government processes. Thai bureaucracy often takes longer than stated timelines. Your current schedule is tight - any slips cascade.

**Q: What if I miss a permit deadline?**

A: Inform authority immediately. Request extension with explanation. Most are flexible if requested early. Don't wait until deadline passes to communicate.

**Q: How do I handle if regulations change?**

A: You don't need to. Thai regulations change infrequently for facilities like this. Your permits lock in conditions as of approval date.

---

# FINAL CHECKLIST - NEXT ACTIONS

## This Week (by July 7)

[ ] Read this summary (30 min)

[ ] Read Navigation Guide (20 min)

[ ] Schedule team meeting to confirm missing permits

[ ] Assign permit manager (if not already done)

[ ] Create action item tracking sheet

## Next 2 Weeks (by July 15)

[ ] Confirm BOI, EIA, FBL status

[ ] Get EIA Approval Certificate (if required)

[ ] Contact AHJ to schedule Building Cert pre-inspection for August

[ ] Finalize water/wastewater designs

[ ] Identify environmental compliance gaps

## End of July

[ ] All design docs ready for Aug submissions

[ ] Equipment orders placed (long-lead items)

[ ] Inspections scheduled for August

[ ] Environmental management plan established

[ ] Waste contractors identified and reserved

[ ] Work permit applications initiated (if needed)

---

# HOW TO ESCALATE ISSUES

**If you discover a permit is missing or delayed:**

1. **Identify the issue** (using documents provided)

2. **Calculate impact** (timeline, cost, operations)

3. **Develop options** (accelerate, redesign, waive if possible)

4. **Escalate to:** Project Manager → Development Director → Client

5. **Timeline:** Any issue >2 weeks impact = escalate immediately

**Example:** "Water supply design not finalized → WHA submission delayed from Aug 9 to Sep 15 → impacts building cert → delays Jan 27 operations by 4-6 weeks → revenue loss 40M THB."

---

# DOCUMENT MAINTENANCE

This documentation package is **current as of June 30, 2026**.

**Update triggers (create new analysis):**

Any permit approval received (update timeline)

Any significant delay discovered (adjust critical path)

Any permit rejected (identify root cause and alternatives)

Quarterly progress review (monthly is recommended)

**Recommended schedule:**

**Weekly:** Permit manager checks 1-2 critical permits

**Monthly:** Full status review against Master Guide

**Quarterly:** Comprehensive update to CHN1A Analysis

---

# TECHNICAL SUPPORT

**If you have questions about:**

---

**END OF DOCUMENTATION SUMMARY**

**Next Step:** Start with the Navigation Guide to orient yourself, then proceed to CHN1A Project Analysis for specific action items.