## Dashboard
PERMIT MANAGER'S DASHBOARD - CHN1A PROJECT
Updated: 2026-06-30 15:21
PERMITS BY PHASE
Development | Total: 5 | Done: | In Progress: | Pending:
Design/Construction | Total: 2 | Done: | In Progress: | Pending:
Construction | Total: 8 | Done: | In Progress: | Pending:
Commissioning | Total: 5 | Done: | In Progress: | Pending:
Operation | Total: 3 | Done: | In Progress: | Pending:
CRITICAL PATH ALERTS
CRITICAL | BOI Certificate | Dependency gate for many permits | In Progress
CRITICAL | EIA Approval | Blocks Building Permit | Not Started
URGENT | Power Confirmation | Grid connection depends on this | Not Started
HIGH | Building Permit | Gates all construction permits | Not Started

## Master List
MASTER PERMIT LIST - ALL 23 PERMITS
# | Permit Name | Authority | Phase | Lead Time (Days) | Status | Planned Start | Deadline | Actual Completion | Owner | Notes
1 | Company Registration | Department of Business Development | Development | 30 | Not Started
2 | BOI Promotion Certificate (if applicable) | Thailand Board of Investment | Development | 120 | Not Started
3 | Foreign Business License (if applicable) | Department of Business Development | Development | 60 | Not Started
4 | Land Use & Zoning Confirmation | Dept of Public Works / Local Authority | Development | 30 | Not Started
5 | Environmental Impact Assessment (EIA) Approval | Office of Natural Resources & Environmental Policy | Development | 180 | Not Started
6 | Building Construction Permit | Local Building Control Authority | Design/Construction | 60 | Not Started
7 | Road Access / Highway Connection Approval | Local Authority / Highway Authority | Construction | 45 | Not Started
8 | Grid Connection Approval | PEA or MEA | Construction | 60 | Not Started
9 | Power Availability Confirmation | Energy Regulatory Commission | Development | 30 | Not Started
10 | High-Voltage Substation Approval | PEA / MEA | Construction | 90 | Not Started
11 | Water Supply Connection Approval | PWA or MWA | Construction | 45 | Not Started
12 | Wastewater / Drainage Connection Approval | Local Authority / Water Authority | Construction | 45 | Not Started
13 | Fire Protection System Approval | Local Building Control / Fire Authority | Construction | 30 | Not Started
14 | Generator & Fuel Storage Approval | Department of Energy Business | Construction | 60 | Not Started
15 | Telecommunications / Fiber Connection Approval | National Broadcasting & Telecommunications Commission | Construction | 45 | Not Started
16 | Electrical Installation Inspection & Energization | PEA / MEA | Commissioning | 14 | Not Started
17 | Fire Safety Inspection | Local Fire Authority | Commissioning | 7 | Not Started
18 | Building Completion Inspection | Local Building Control Authority | Commissioning | 7 | Not Started
19 | Occupancy Certificate / Building Use Permit | Local Building Control Authority | Commissioning | 14 | Not Started
20 | Commissioning & Utility Acceptance | Utilities and Local Authorities | Commissioning | 21 | Not Started
21 | Factory License (if applicable) | Department of Industrial Works | Operation | 30 | Not Started
22 | PDPA Compliance | Personal Data Protection Committee | Operation | 30 | Not Started
23 | Cybersecurity Compliance (Critical Infrastructure) | National Cyber Security Agency | Operation | 30 | Not Started

## Authority Contacts
AUTHORITY CONTACT INFORMATION
Authority Name | Phone | Email | Office Address | Coordinator Name | Office Hours | Website
Department of Business Development (DBD) | +66-2-547-3000 | info@dbd.go.th | Bangkok | TBD | 08:30-16:30 | www.dbd.go.th
Thailand Board of Investment (BOI) | +66-2-553-8111 | inquiry@boi.go.th | Bangkok | TBD | 08:30-16:30 | www.boi.go.th
Office of Natural Resources & Environmental Policy (ONEP) | +66-2-535-8800 | inquiry@onep.go.th | Bangkok | TBD | 08:30-16:30 | www.onep.go.th
Local Building Control Authority | TBD | TBD | Local | TBD | TBD | TBD
Provincial Electricity Authority (PEA) | +66-2-399-9999 | TBD | Regional | TBD | TBD | www.pea.co.th
Metropolitan Electricity Authority (MEA) | +66-2-246-3888 | TBD | Bangkok | TBD | 08:30-16:30 | www.mea.or.th
Energy Regulatory Commission (ERC) | +66-2-553-8511 | TBD | Bangkok | TBD | 08:30-16:30 | www.erc.or.th
Provincial Waterworks Authority (PWA) | +66-2-503-9000 | TBD | Regional | TBD | 08:30-16:30 | www.pwa.co.th
National Broadcasting & Telecommunications Commission (NBTC) | +66-2-575-9000 | TBD | Bangkok | TBD | 08:30-16:30 | www.nbtc.go.th
Department of Energy Business (DOEB) | +66-2-553-6500 | TBD | Bangkok | TBD | 08:30-16:30 | www.doeb.go.th
Department of Industrial Works (DIW) | +66-2-547-1310 | TBD | Bangkok | TBD | 08:30-16:30 | www.diw.go.th
National Cyber Security Agency | +66-2-141-2999 | TBD | Bangkok | TBD | 08:30-16:30 | TBD
Personal Data Protection Committee | TBD | TBD | Bangkok | TBD | TBD | TBD

## Action Items
ACTION ITEMS & TASKS - THIS WEEK
Task | Permit # | Owner | Due Date | Priority | Status | Notes
Verify ERC Power Confirmation Letter | 9 | TBD | 2026-06-30 | CRITICAL | In Progress | Prerequisite for BOI
Complete BOI Application Documents | 2 | TBD | 2026-07-07 | CRITICAL | In Progress
Submit EIA Screening | 5 | TBD | 2026-07-03 | CRITICAL | Not Started
Prepare FBL Documents | 3 | TBD | 2026-07-14 | HIGH | Not Started | After BOI approval
Contact DBD for Company Registration | 1 | TBD | 2026-07-01 | HIGH | Not Started

## Risks & Issues
RISKS & ISSUES BLOCKING PERMITS
Permit # | Issue/Blocker | Severity | Owner | Mitigation Plan | Status | Target Resolution Date | Notes
9 | ERC power confirmation delayed | CRITICAL | TBD | Escalate to Thailand FastPass | In Progress | 2026-07-07 | Gate for BOI application
5 | EIA study scope unclear | HIGH | TBD | Clarify with ONEP | Not Started | 2026-07-14
2 | BOI capital requirements | MEDIUM | TBD | Verify THB 2B+ threshold met | Not Started | 2026-07-07